| # Design Sprint Light for Advantage Nordic | ### Dates: Enter date(s) |
| --- | --- |
| ### Sprint background Advantage Nordic has previously done an AI Driven Discovery & Prototyping workshop where they worked on an idea to create a product to proactively use AI to suggest deals for companies to take advantage of for purchasing business supplies. | ### Sprint team (5-7 people) Name; Role. Nicolas Wainach; Role. Pelle Sørensen; Role. Anette Wiraas Karlsen; Role. Sofia Ekberg; Nordic Product Delivery Manager. Audun Kleveland; Role. Catalin Sandru; Product Design Lead. Julie Rasmussen; Facilitator. Radu Dragos; Facilitator. Lucia Wang; Facilitator. |
| ### Sprint challenge How might we use AI to enhance purchasing business supplies in a proactive way for procurement responsibles to increase total everyday spend across more partner agreements |  |

Note: Aim for a diverse sprint team, focusing on the product team that will develop the solution.

| ### Experts (3 people) | Who are the experts that can help us understand the challenge scope? |  |
| --- | --- | --- |
| ### Name | Role | Customer name |
| Name | NO salesperson | Internal |
| Name | SE Salesperson | Customer name |
| Name | SE Customer | Customer name |
| Name | NO Customer | Customer name |
| Note: Experts can be external or internal based on what we need to learn. The input from the experts help us make sure we are focusing on the right things. |  |  |

| ### Usability testers (5 people) | Who are the end-users? Aim for diversity. |  |
| --- | --- | --- |
| ### Name | Role | Customer name |
| Name | SE customer | Customer name |
| Name | NO customer | Customer name |
| Name | NO customer | Customer name |
| Name | SE customer | Customer name |
| Name | DK customer? | Customer name |

# Day by day schedule

### Day 1: Define the challenge and and map the optimal user journey

| Time | Activity |
| --- | --- |
| 09:00 - 09:15 | Intro |
| 09:15 - 09:30 | Align on the sprint challenge |
| 09.30 - 10.30 | Aligning on previous work with high level team |
| 10:30 - 11.00 | Define long-term goals and potential blockers and revisit the challenge |
| 11:00 - 11:15 | Decide what we want to ask the experts and prepare for How Might We exercise |
| 11:15 - 12:00 | Lunch |
| 12:00 - 13:30 | Expert interviews 12:00 - 12:20 NO kund - Volat/ Mario 12:25 - 12:45 SE expert - Almir 12:50 - 13:10 SE kund - Etteplan/ Torgny 13.15 - 13:30 NO expert Thoams |
| 13:30 - 13:45 | Break |
| 13:45 - 14:30 | Organise HMW’s from the interviews and revisit the challenge |
| 14:30 - 16:00 | ç |

Note: Experts can be external or internal based on what we need to learn. 
The input from the experts help us make sure we are focusing on the right things.

### Day 2: Sketch and storyboard

| Time | Activity |
| --- | --- |
| 09:00 - 10:00 | User journey recap and alignment with high level team |
| 10:00 - 10:45 | Detail the AI opportunities |
| 10:45 - 11:00 | Break |
| 11:00 - 11:30 | Lightning demos |
| 11:30 - 13:00 | Sketching + Lunch |
| 13:00 - 13:30 | Presentations and voting |
| 13:30 - 14:30 | Sketching |
| 14:30 - 14:45 | Break |
| 14:45 - 15:15 | Presentations and voting |
| 15:15 - 16:00 | Create a storyboard matching the optimal user journey |

Note: The sketches act as the input for the prototype. 
It is therefore important that everyone contributes as best they can.

### Day 3: Prototype and prepare for usability tests

| Time | Activity |
| --- | --- |
| 09:00 - 10:00 | Alignment with high level team |
| 10:00 - 11:30 | Prepare usability test script |
| 11:30 - 12:30 | Lunch |
| 12:30 - 13:30 | Prepare scorecard |
| 13:30 - 14:00 | Align on prototype |
| 15:30 - 16:00 | Align on prototype |

Note: Part of the team will spend the full day prototyping. Having prototype check-ins will 
ensure that you are aligned and allow all team members to contribute to the prototype.

### Day 4: Usability testing and retrospective

| Time | Activity |
| --- | --- |
| 08:30 - 09:30 | Make sure that everything is ready for testing |
| 09:30 - 10:25 | Usability test with User 1 - Tom at isiflo |
| 10:30 - 11:25 | Usability test with User 2 - Kristian at Aura |
| 11:30 - 12:30 | Lunch |
| 12:30 - 13:25 | Usability test with User 3 |
| 13:30 - 14:25 | Usability test with User 4 |
| 14:30 - 15:25 | Usability test with User 5 |
| 15:30 - 15:45 | Break |
| 15:45 - 16:00 | Fill out retrospective exercise |
| 16:00 - 16:30 | Retrospective and alignment with high level team |

Note: Test day is the most fun day! Having the retrospective at the end of the day allows 
team members to note down their top findings while they are still fresh, and settle on next steps.